This document has been produced in accordance with the requirements of the Welsh Language (Wales) Measure 2011 and specifically the following standards:

155/156/157/159/161/162/163/165/167/168/169/171/173/175

WELSH LANGUAGE STANDARDS: COMPLIANCE AND MONITORING REPORT 30th APRIL 2019

This table has grouped the Standards into themes for ease of reference.  A full list of the standards is available at:  http://www.monmouthshire.gov.uk/app/uploads/2017/01/20160801-Hysbysiad-Cydymffurfio44-Cyngor-Sir-Fynwy-cy.pdf  Please note that this list is not exhaustive and highlights areas that potentially required further work. It should be noted that we are already compliant with many of the standards while others can be implemented with minimal change to systems.

| Standards Relating to: | Summary of new expectations created by the standard | Risks / Challenges for MCC | Actions Required / Options to consider to ensure we meet the standards | Progress Update |
| --- | --- | --- | --- | --- |
| Written correspondence (Standards 1-7) | All correspondence should state that people can respond to us in Welsh and that corresponding in Welsh will not lead to a delay. We must keep a record of peoples language preference and use that language in all future correspondence (30 Sept) | Providing a timely response where the initial correspondence and reply both need to be translated externally. Maintaining an accurate record of language preferences across multiple ICT systems that hold client records. | - Identifying options to enable fast-tracking of certain translation requests. - Explore the most cost effective arrangement to procure increased volume of translation including direct employment of a translator - Develop an approach to capture language preferences and ensure a (manual) interface with existing records. - All letters and e mails should have a strapline – corresponding in welsh will not lead to delay. | A grading system is used which denotes the level of urgency and works very efficiently indeed. (Level 1 Urgent – 1 day. Level 2 moderate 2 – 5 days. Level 3 no specific end date or urgency) Currently the council procure the services of 7 external translators and the system is working well. This system is monitored on a daily basis by the (WLO) Welsh Language Officer. The council did explore the possibility of an in-house translation service provision but the figures in the business case indicated that the current system is the most effective in both financial and efficiency terms. The WLO is eagerly awaiting developments on a database that can cope with these requirements Strapline actioned. |
| Telephony, hubs and reception (Standards 8 – 22 and 64-68) | We are expected to offer: a Welsh language telephone service in our contact centre by 30 March; Welsh language reception in Usk by 30 March and all other receptions by 30 September.2017 – extension agreed by Commissioner We must keep a record of language preference for phone calls (30 Sept) | A low number of staff who are Welsh speakers (c.31) Staff turnover in these functions is low so it will take a while to get Welsh speakers in post. Names of Welsh speakers from Monmouthshire have been added to the language preference database | - Train Staff on reception and in Hubs (Welsh Language Officer is the lead) - Workforce planning required. - Create a telephone ‘loop’ or hunt system with calls being redirected to the first available Welsh speaker regardless of physical location or team – | In 2018-19, we ran the following Welsh Language sessions and financially supported (including fees and books) individuals who attended classes after work and weekend refresher courses in their own time:- 31 members of staff signed up for the Cwrs Mynediad Year 1 Cymraeg yn y Gweithle 2 hour 30 week course provided by Coleg Gwent Welsh for Adults. These were supplemented by 7 members of the public who joined the classes. 17 members of staff signed up for second year of the Cwrs Mynediad course. 2 members of staff were funded to attend Cwrs Mynediad after work 1 member of staff was funded to attend year 2 Mynediad after work 1 member of staff was funded to attend year 1 Fast track course 2 members of staff were funded to attend year 3 Sylfaen 5 members of staff from Severn View were given bespoke carer training through the medium of Welsh 14 members of staff have signed up to the free 10 hour Cwrs Croeso Staff are funded to attend Coleg Gwent Welsh Weekend Courses in addition to weekly courses. More classes will be offered in September 2019 The Welsh Language Officer continues to work through the Workforce Planning exercise and below is the current list of the divisions that have gone through the process: Human Resources, Contact Centre, Libraries and Hubs in the north and south of the county, Policy and Performance, Community Partnerships Development Team, Youth Services, Planning, Building Control, Housing, Communication and Engagement, Leisure Services (part), Waste Services, Environmental Health. The response from managers to the above process remains positive with increasing numbers of future vacancies highlighted as requiring Welsh Essential designation and the posts mentioned below are signs that the process is starting to bear fruit. Our Welsh Language Line remains popular. Having been established on the 4th July 2017 we have had in total 243 calls in total despite the number of calls being very few in the early months. The following are the figures for the last financial year: 1st April 2018 – 31st March 2019 – 87 calls in total The following is a list of the service required or the nature of the phone calls received by the Welsh line in the last financial year. This list will be useful when carrying out the ongoing Workforce Planning exercise in order to assist in the decision making process for differentiating between Welsh essential or desirable designations in vacancies. - Welsh Language Officer 5 - Refuse 19 - Communications Team 9 - Council Tax 4 - Grass Routes/Passenger Transport 17 - Education 7 - Health and Safety 1 - Operations 3 - Events 3 - Social care 2 - Creditors 2 - Sports development 1 - Planning 2 - Leisure 1 - Environmental Health 1 - Elected members 2 - Social Care 1 - Freedom of Information 1 - Street Lighting 2 - Housing 1 - Chief Executive 1 - Other n/k 2 Welsh language Signs are placed in each reception and all Welsh language speakers wear a badge. This is monitored by the WLO in collaboration with service managers. |
| Welsh in meetings (Standards 24 – 34) | We must advertise that people are able to use Welsh at meetings. If 10% of attendees choose to use Welsh then we must provide simultaneous translation. If a meeting involves only one member of the public/business/partner and they wish to use Welsh then we must provide translation. Invitations to any public meetings must be bilingual and specify that people can use Welsh | People will need to give advance notice, however simultaneous translation is likely to be in short-supply after the standards come into effect. | Identify the most cost-effective arrangement for simultaneous translation and put a call-off contract in place if required Ensure that all officers are aware of this requirement and incorporate it into their letters and public notices | - A process is in place with a list of simultaneous translators that can be procured. - A sample audit has revealed that we are compliant in terms of Planning and Democratic Services. - The Welsh Language offer is stated on all Council agendas and agenda packs on both Welsh and English versions of the council websites. |
| Public events (Standards 35-38, 87) | Public events such as festivals should use bilingual publicity material, signage and PA announcements, this applies if we provide over 50% of the funding. Welsh should be used first (after 30 Sept). Any publicity or advertising material should also be available in Welsh e.g. promotional films | The relatively low numbers of Welsh speakers in the area may make it difficult to attract bilingual announcers – especially where volunteers are used. | Ensure that events teams are fully aware of the requirements of the Act. | - Events staff have attended the bespoke training sessions and are aware of the requirements |
| Papers for council business (Standard 41) | Agendas and minutes of any council meetings available to the public should be bilingual | The original standard suggests reports presented to meetings should also be bi-lingual. However MCC has requested and received an exemption to this. Potential delays in despatch of agendas. | Ensure that minutes are an accurate and concise record of the meeting to minimise translation costs | - All agendas for Cabinet, Council and Scrutiny Committees are produced bilingually at the same time as the English version of the agenda. - This process is facilitated and monitored by the WLO in collaboration with the Democratic Services Manager. |
| Licensing (Standard 42) | Any licenses or certificates must be bilingual |  | Ensure that all licenses are bilingual when new ones are issued | - Licensing Department are compliant with everything in place. - Planning notices are all bilingual – on lamp posts and in the local press. - This is monitored by the WLO |
| Documents (Standards 43 – 50B) | Any brochures or leaflets providing public information should be published in Welsh including rules; all forms should be bilingual; press releases should be issued in Welsh at the same time as the English. Policies, Strategies and annual reports will need to be available in Welsh by 30 September | We are likely to experience delays translating forms received in Welsh where staff are not Welsh speakers. Our current translation service is not instantaneous resulting in potential delays to the issue of Welsh versions after the English There is low demand for some strategy documents amongst the public | Where we produce separate versions of a document the English version should state that it is also available in Welsh. | - The Web Officer and the Welsh Language Officer work closely to monitor that corresponding pages are present on the website and chase up individuals if there are any anomalies – these do occur from time to time but are swiftly addressed. |
| Websites and Social Media (Standards 52 – 59) | All webpages must be available in Welsh (by 30 March). All corporate tweets and Facebook posts from MCC accounts must be issued in Welsh (by 30 Sept) | Delays in translating posts may reduce the timeliness of our response. Any delays in posts while awaiting translation could reduce their usefulness e.g. snow closures, traffic announcements | Identifying options to enable fast-tracking of certain translation requests. Ensure that all staff managing social media accounts are fully aware of the need to run these bilingually | - A grading system has been developed to indicate the urgency of translation. This allows for the correct timescales for translation. - A Welsh Language Facebook account and bilingual Twitter accounts have been developed by the Web Officer. - The process is monitored by the council’s communications staff and the WLO. |
| Signage (Standard 61 – 63) | There is an expectation that when new signs, including road signs, are replaced, the Welsh should precede the English | Risk that a phased approach could cause confusion for motorists as there will be an inconsistency of language placement in the medium term |  | - Processes are in place – very good historical level of compliance and no concerns. - The only area of slight concern are occasional issues over disputed Welsh versions of local place names. The Gazeteer from the old Welsh Language Board is used as the arbiter in these instances. This process is dealt with and monitored by the WLO |
| Official Notices (Standards 69-70) | All official notices should be bilingual with Welsh treated no less favourably than the English | Bilingual press notices will increase the number of column inches of advertising we buy | Identify alternative options for publishing public notices to minimise cost increases | - Monitoring of local press undertaken by WLO and there are no concerns to report. |
| Grants and tenders (Standards 71 – 80, 94) | Grant documents must be bilingual, we must provide simultaneous translation where requested, if a grant applicant wishes needs to be interviewed. We should advertise that any tenders can also be submitted in Welsh. |  |  | - The language choice of the tender applicants is being sought in order to allow to provide documents in the tenderers language of choice. |
| Education Courses (Standard 84-86) | Courses open to the public must also be made available in Welsh. | MCC has an exemption to this standard providing we can evidence there is no need for a particular course to be offered in Welsh | Ensure that the public are made aware that they can express a preference for a course to be delivered in Welsh. We must collate evidence of the need for the course to be provided in Welsh. It would only be provided if there were sufficient demand | - All bilingual Community Education course application forms have a section to allow Welsh Language preference to be expressed on them to allow an assessment to be made. - No requests for Welsh language provision to date. - This process is carefully monitored by Community Education staff. |
| Policy-Making (Standards 88 – 97) | Policy-making must take into account the effect on the Welsh language to maximise positive effects and minimise adverse effects. | There is potential for legal challenge of decision if we are unable to demonstrate the application of the standards to policy making | Ensure that the Future Generations Assessment (Sustainability and Equality Impact) effectively identifies any implications on the Welsh language | - Implicit within the Future Generation/EQIA process. The Welsh Language has always been treated as the 10th protected characteristic and is an integral part of the process. |
| HR Issues (Standards 98 – 119) | We must produce a policy on internal use of Welsh; offer communication relating to employment in Welsh including forms and e-forms. | HR systems are produced by a national suppler and are not available in Welsh should the demand materialise | Translate key documents | - All Welsh speaking staff in the council have been asked whether they would like any of their employment documentation through the medium of Welsh. No responses for Welsh documentation were received. |
| Welsh in the workplace (Standard 120 – 135, 140-144) | We must provide opportunities for basic Welsh training for employees during office hours and meet the cost of courses for those who already have basic Welsh to develop their skills. Provide Welsh language versions of software where available such as Welsh language spell checkers in word-processing packages (by 30 Sept) | Although offering clear long-terms advantages this has the potential to reduce the operational capacity in the short-term if take-up is high. | . | Same as Telephony, hubs and reception (Standards 8 – 22 and 64-68) above - 10 licences of Gysgair and Cysillt were purchased from Canolfan Bedwyr in Bangor, and all fluent Welsh speakers have been contacted personally to ask whether they wanted a copy. |
| Recruitment and Selection (Standards 136-140) | Recruitment and all job descriptions must be made available in Welsh; if forms are submitted in Welsh they should not be treated less favourably; people may request simultaneous translation if they wish to be interviewed through the medium of Welsh | Simultaneous translation is likely to be in short-supply after the standards come into effect. | Ensure that all forms and processes are updated in accordance with the standards | - All vacancy documentation has historically been in place - All external vacancies include a Welsh language assessment – Essential, desirable or not required. - In the case of essential or desirable assessments the advert, Job description and person specification must be translated. - Where there is no language requirement only the job description needs to be translated. HR have produced and distributed templates to managers to save time and reduce translation costs. This process is being led by the WLO in partnership with HR |
| Overseeing the Language Scheme: Record-keeping, reporting and complaints (Standards 145 – 176) | There is a requirement to keep a range of records to demonstrate compliance with the standards and to publish (in Welsh) an annual report demonstrating compliance. Publish a five year strategy to show how we plan to promote the Welsh Language | There will be no direct costs, however these standards will create an administrative pressure | Ensure that systems are set up to keep records in accordance with the standards. | - Everything in place and has been for many years due to the old Welsh Language Scheme and its requirement to produce an Annual Monitoring Report. - The councils 5 year strategy was agreed by Council on the 19th January 2017 and sits on its website – Welsh and English. - All the above is both monitored and actioned by the WLO |

COMPLAINTS PROCEDURE IN RELATION TO THE WELSH LANGUAGE:

The complaints procedure for specific to issues with Service delivery, policy making and operational standards and issues of non-compliance in accordance with the council’s Welsh Language Standards follow the same set of timescales and processes as the corporate process (link below) but there are some variations that are worth noting:

Complaints can be sent in and dealt with in two different ways:

Complaint sent directly to the Council where the complaint will be dealt with the service department. If there is not the language skills available within the department to deal with the issue then the Welsh Welsh Language Officer will liase to allow Language choice for the complainant and then hopefully to resolve the issue to the satisfaction of both parties. If a resolution is not reached then the process to escalate the complaint is explained clearly in the corporate document linked below.

Direct to the Welsh Language Commissioner. This will trigger a suspicion of non-compliance notice that will lead to a ten stage/three month investigation process that will hopefully resolve any issues satisfactorily.